## Slide 1: Corrin 2028 adds $104m of EBITDA and releases $146m of working capital by FY2028; the board is asked to approve the programme, two plant exits and the $165m it costs
Corrin Medical
Board of Directors | Corrin 2028 operating transformation | 18 December 2025 | Illustrative figures for a fictional company
1
BOARD DECISION | CORRIN 2028
Three approvals asked of the board
1
Programme. Approve Corrin 2028 and the $165m to deliver it: $98m of one-off cost and $67m of capital, $72m of it in 2026.
2
Footprint. Approve the exits of Salt Lake City by September 2027 and Tuttlingen by June 2028, subject to consultation.
3
Operating model. Approve a shared-services hub in Brno, global procurement, and quality and regulatory reporting to the CEO.
If approved, the programme launches in January 2026 at M1, and the board reviews it at each of five further milestones to December 2028.
What it costs and when it pays back
$m | 2026 | 2027 | 2028 | Total
One-off operating cost | 44 | 36 | 18 | 98
Capital expenditure | 28 | 25 | 14 | 67
Cost to achieve | 72 | 61 | 32 | 165
Net cash after cost | (16) | 52 | 99 | 135
Cumulative net cash | (16) | 36 | 135 | 
Cash turns positive in 2027 because working capital is released ahead of the full run-rate.
In this pack
Page | What it proves
2 | Order to cash: 70 days today, six pain points costing $28m a year
3 | Footprint: seven plants become five; utilisation from 64% to 84%
4 | Prioritisation: fourteen initiatives on value, ease and cost
5 | Value bridge: $186m to $290m of EBITDA, and the cash case
6 | Roadmap: 2026 to 2028, six milestones, three dependencies
7 | Operating model: five new units, two fewer layers
8 | Risks: nine scored before and after mitigation
Eight commitments for FY2028
FY2028 target in petrol and its change from the FY2025 baseline; bars show FY2025, the FY2026 and FY2027 interim targets and FY2028 on one scale; the page that proves each, top right
Run-rate EBITDA
p. 5
$290m
+$104m from $186m
FY25
$186m
FY26
$217m
FY27
$256m
FY28
$290m
$103m from four levers and $38m from volume, less $37m of inflation and run costs
Owner: CFO
Initiatives: all twelve
EBITDA margin
p. 5
20%
+5 pts from 15%
FY25
15%
FY26
17%
FY27
19%
FY28
20%
EBITDA grows faster than revenue, which rises 5.4% a year to $1,450m
Owner: CFO
Initiatives: all twelve
Order-to-cash days
p. 2
51
-19 days from 70
FY25
70
FY26
64
FY27
57
FY28
51
Avoidable delay falls from 25 to 6 days, releasing $75m of receivables
Owner: CFO
Initiatives: C1 to C3, O1
Inventory days
p. 5
105
-37 days from 142
FY25
142
FY26
131
FY27
117
FY28
105
One global plan across five plants releases $71m of stock
Owner: COO
Initiatives: F3, planning
On time, in full
p. 6
96%
+9 pts from 87%
FY25
87%
FY26
90%
FY27
93%
FY28
96%
One global supply chain; lines dual- qualified before each move
Owner: COO
Initiatives: F1 to F3
Network utilisation
p. 3
84%
+20 pts from 64%
FY25
64%
FY26
67%
FY27
76%
FY28
84%
Steps up in 2027 as Salt Lake City closes, and again with Tuttlingen
Owner: COO
Initiatives: F1, F2
Invoice lines priced right
p. 2
99.5%
+6.7 pts from 92.8%
FY25
92.8%
FY26
96.5%
FY27
98.8%
FY28
99.5%
One contract-price master replaces 12 hand-kept GPO price lists
Owner: CCO
Initiatives: C1
G&A cost, % of revenue
p. 7
9.4%
-2.2 pts from 11.6%
FY25
11.6%
FY26
11.1%
FY27
10.2%
FY28
9.4%
Brno hub, 190 fewer G&A roles and two fewer management layers
Owner: CFO
Initiatives: O1, O2
Source: Corrin Medical management accounts and transformation plan; FY2025 is eleven months actual and a December forecast. All figures are illustrative, invented for a fictional company.
Notes: All figures on this page are illustrative: Corrin Medical is a fictional company and every number was invented and computed for this example. The ask is three approvals: the programme and its $165m, the two plant exits, and the operating model. Walk the eight commitments left to right; each names the page that proves it.

## Slide 2: Order-to-cash takes 70 days, 25 beyond contract terms; six pain points cost $28m a year
Corrin Medical
Board of Directors | Corrin 2028 operating transformation | 18 December 2025 | Illustrative figures for a fictional company
1
DIAGNOSIS | ORDER TO CASH
The cycle today: seven steps, 70 days from order to cash, 58.8 of them in Collect
Average days per order and the share of orders handled by hand at each step; FY2028 target in petrol; the dominant step in orange
1 Capture order
2 Price and credit
3 Allocate and pick
4 Ship, confirm use
5 Invoice
6 Collect
7 Apply cash
Per order |  |  |  |  |  |  | 
Days, FY2025 | 0.9 | 1.6 | 1.2 | 3.1 | 2.4 | 58.8 | 2.0
Days, FY2028 target | 0.2 | 0.3 | 0.8 | 1.6 | 0.2 | 47.5 | 0.4
Handled by hand, FY2025 | 41% | 36% | 22% | 30% | 18% | 25% | 28%
Handled by hand, FY2028 | 10% | 8% | 15% | 12% | 3% | 8% | 6%
Six pain points cost $28m a year
Numbers match the orange marks on the flow; cost is annual leakage, rework and write-off
# | Step | Pain point and evidence | $m a year | Fixed by
1 | 1 Capture order | 41% of orders arrive by fax or e-mail and are re-keyed; 3.8% carry an entry error | 3.1 | O1, C1
2 | 2 Price and credit | 12 GPO price lists kept by hand; 7.2% of invoice lines priced wrong | 14.6 | C1
3 | 4 Ship, confirm use | Bill-only implant use reported 9.0 days after surgery; consignment counted by hand | 2.8 | C2
4 | 5 Invoice | Invoices issued 2.4 days after shipment; 18% need a manual release | 1.2 | O1
5 | 6 Collect | 9.4% of invoices disputed, 34 days to resolve: 13.8 days past terms | 4.9 | C3
6 | 7 Apply cash | 28% of remittances matched to invoices by hand | 1.4 | C3
 | Total |  | 28.0 | 
Four initiatives remove them
C1 Contract-price master
$10m run-rate for $7m; live in the US in May 2026; fixes pain point 2 and the pricing half of 1
C2 Bill-only digitised
$4m for $8m; surgeons' implant use reported from the theatre on the day of surgery: pain point 3
C3 Collections automation
$4m for $6m; disputes routed by cause and cash matched by rule: pain points 5 and 6
O1 Brno hub
Order entry and invoicing move to one team in January 2027, removing the re-keying in pain points 1 and 4
Where the 70 days go
Average days from order to cash: pale, contract terms, unchanged; orange, avoidable delay
Chart: 
| FY2025 | FY2028 target
Contract terms | 45 | 45
Avoidable delay | 25 | 6
Avoidable days, by where they arise | FY2025 | FY2028
Collect past contract terms, step 6 | 13.8 | 2.5
Processing in the other six steps | 11.2 | 3.5
Avoidable delay | 25.0 | 6.0
Cutting 19 avoidable days releases $75m of receivables at FY2028 revenue. The C initiatives capture $18m of the $28m a year, 64%.
Source: Corrin Medical management accounts and transformation plan; FY2025 is eleven months actual and a December forecast. All figures are illustrative, invented for a fictional company.
1
2
3
4
5
6
Notes: All figures on this page are illustrative: Corrin Medical is a fictional company and every number was invented and computed for this example. Collect includes the 45 contractual days; only the 13.8 days past terms are avoidable there. Pricing errors at step 2 are the largest leak at $14.6m a year.

## Slide 3: Two plant exits lift network utilisation from 64% to 84% and save $29m a year
Corrin Medical
Board of Directors | Corrin 2028 operating transformation | 18 December 2025 | Illustrative figures for a fictional company
1
FOOTPRINT | SEVEN PLANTS TO FIVE
Two regional clusters, two closures, three line transfers
Each closing plant's lines go to the nearest plant that already makes or services the product
North America
Europe
Plant that closes
Plant retained or expanded
Production lines move
Salt Lake City's pump electronics move to Minneapolis and its infusion sets to Ciudad Juarez; Tuttlingen's instruments move 590 km to Brno, which already reprocesses them.
84%
Network utilisation in FY2028, capacity-weighted, from 64%
9 lines
Moved in three transfers, one at a time, by June 2028
-150
Net headcount: 4,020 to 3,870, as receiving plants hire 550
Capacity, utilisation and headcount by plant
Capacity is annual output at standard cost; utilisation is output over capacity; FY2028 in petrol, closing plants in orange
 |  | Capacity, $m |  | Utilisation, % |  | Headcount |  | 
Plant | Products | FY25 | FY28 | FY25 | FY28 | FY25 | FY28 | Action
Minneapolis | Monitoring systems | 260 | 290 | 66 | 86 | 640 | 760 | Expand: pump electronics
Salt Lake City | Infusion pumps | 150 | - | 48 | - | 410 | - | Exit by September 2027
Ciudad Juarez | Infusion sets | 300 | 360 | 79 | 88 | 980 | 1,150 | Expand: infusion sets
Alajuela | Catheters | 210 | 210 | 70 | 81 | 720 | 760 | Retain
Galway | EU sterile catheters | 190 | 190 | 66 | 78 | 530 | 560 | Retain
Tuttlingen | Surgical instruments | 110 | - | 41 | - | 290 | - | Exit by June 2028
Brno | Reprocessing | 160 | 200 | 52 | 80 | 450 | 640 | Expand: instruments
Network | Seven plants to five | 1,380 | 1,250 | 64 | 84 | 4,020 | 3,870 | 
Capacity falls by $130m to $1,250m: the network loses its two least-used plants, at 48% and 41%, and fills the rest.
Three line transfers, one at a time
Lines moved | From | To | Validation | Cut-over
Pump electronics, 2 lines | Salt Lake City | Minneapolis | Jan to Apr 2027 | June 2027
Infusion sets, 3 lines | Salt Lake City | Ciudad Juarez | Mar to Jul 2027 | September 2027
Surgical instruments, 4 lines | Tuttlingen | Brno | Oct 2027 to Mar 2028 | June 2028
Each line runs 10 to 12 weeks of bridge stock through its cut-over; validation is re-qualification under the receiving plant's quality system.
The $29m saving pays back the $68m in 2.3 years
Footprint initiative | Run-rate saving, $m | One-off cost, $m | Payback, years
F1 Salt Lake City exit | 15 | 38 | 2.5
F2 Tuttlingen exit to Brno | 9 | 24 | 2.7
F3 Lean and OEE in retained plants | 5 | 6 | 1.2
Footprint lever | 29 | 68 | 2.3
Payback is one-off cost and capital over the run-rate saving; F1's saving starts at M4 in September 2027 and F2's at M5 in June 2028.
Source: Corrin Medical management accounts and transformation plan; FY2025 is eleven months actual and a December forecast. All figures are illustrative, invented for a fictional company.
Minneapolis
Salt Lake City
Ciudad Juarez
Alajuela
Galway
Tuttlingen
Brno
Notes: All figures on this page are illustrative: Corrin Medical is a fictional company and every number was invented and computed for this example. The pairing is geographic: each closing plant's lines go to the nearest plant that already makes or services the product. Payback is the one-off cost over the run-rate saving. Map outlines and lakes are Natural Earth, public domain.

## Slide 4: Four strategic bets hold 46% of the value and 64% of the cost; two quick wins start now
Corrin Medical
Board of Directors | Corrin 2028 operating transformation | 18 December 2025 | Illustrative figures for a fictional company
1
PRIORITISATION | INITIATIVES
Value against ease of delivery, sized by cost
Each point is one initiative by code: strategic bets in orange, other initiatives in petrol, deferred ideas in grey
Quick wins
Strategic bets
Fill-ins
Defer unless enabling
Chart: Ease of delivery, 1 hard to 5 easy
| 2.3
Strategic bets, 7pt | 11
Strategic bets, 11pt | 9
Strategic bets, 15pt | 15 | 12
Other initiatives, 7pt | 16 | 7 | 5 | 10 | 4 | 4 | 7
Other initiatives, 11pt | 3
Deferred | 2 | 3
Marker size is the cost to achieve:
under $10m
$10m to $25m
over $25m
Twelve initiatives in the plan
Run-rate EBITDA and cost to achieve, $m; ease scored 1 hard to 5 easy; strategic bets in orange
Code | Initiative | $m EBITDA | $m cost | Ease | Quadrant | Wave
P1 | Direct-material re-sourcing | 16 | 6 | 3.8 | Quick win | 1
P2 | BOM value engineering, top 20 SKUs | 11 | 9 | 2.3 | Strategic bet | 2
P3 | Indirect spend and freight tender | 7 | 2 | 4.4 | Fill-in | 1
F1 | Salt Lake City exit | 15 | 38 | 1.8 | Strategic bet | 2
F2 | Tuttlingen exit to Brno | 9 | 24 | 2.2 | Strategic bet | 3
F3 | Lean and OEE in retained plants | 5 | 6 | 4.0 | Fill-in | 1
C1 | Contract-price master, GPO compliance | 10 | 7 | 4.2 | Quick win | 1
C2 | Bill-only and consignment digitised | 4 | 8 | 3.3 | Fill-in | 2
C3 | Collections and dispute automation | 4 | 6 | 3.6 | Fill-in | 1
O1 | Shared-services hub, Brno | 12 | 34 | 2.7 | Strategic bet | 2
O2 | Spans and layers, commercial and G&A | 7 | 9 | 3.4 | Fill-in | 1
O3 | Global quality and regulatory function | 3 | 16 | 2.4 | Enabler | 1
 | Total, twelve initiatives | 103 | 165 |  |  | 
The four strategic bets, P2, F1, F2 and O1, carry $47m of the $103m, 46%, and $105m of the $165m cost, 64%: they are where delivery risk sits.
The quick wins, P1 and C1, add $26m for $13m and start in January 2026. Wave 1 is seven initiatives worth $52m for $52m of cost, all started by April 2026.
Deferred: X1 own distribution in DACH ($2m, ease 1.5) and X2 single-step ERP replacement ($3m, ease 1.2).
By lever: what each dollar of EBITDA costs
Lever | $m EBITDA | $m cost | Cost per $ of EBITDA
Procurement, P1 to P3 | 34 | 17 | 0.50
Footprint, F1 to F3 | 29 | 68 | 2.34
Commercial and order to cash, C1 to C3 | 18 | 21 | 1.17
Operating model, O1 to O3 | 22 | 59 | 2.68
Total | 103 | 165 | 
Source: Corrin Medical management accounts and transformation plan; FY2025 is eleven months actual and a December forecast. All figures are illustrative, invented for a fictional company.
Ease 3
$8m
Notes: All figures on this page are illustrative: Corrin Medical is a fictional company and every number was invented and computed for this example. Ease combines technical, regulatory and people complexity on a 1 to 5 scale scored by the Transformation Office. Quick wins are P1 and C1; marker size groups the cost to achieve.

## Slide 5: Volume offsets inflation and run costs; four levers add $103m, taking EBITDA to $290m
Corrin Medical
Board of Directors | Corrin 2028 operating transformation | 18 December 2025 | Illustrative figures for a fictional company
1
VALUE | EBITDA BRIDGE AND CASH
FY2025 EBITDA to FY2028 exit run-rate, $m
Totals in dark petrol, increases in mid petrol, decreases in grey; volume first nets off inflation and run costs; cost to achieve under each lever
Chart: 
| FY2025 EBITDA | Volume and mix | Inflation | Run costs | Procurement | Footprint | Commercial, O2C | Operating model | FY2028 run-rate
Base | 0 | 186 | 193 | 187 | 187 | 221 | 250 | 268 | 0
Step | 186 | 38 | 31 | 6 | 34 | 29 | 18 | 22 | 290
Label | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBITDA builds over three years
Run-rate at each year end, $m; margin on that year's revenue
$m, run-rate at year end | 2025 | 2026 | 2027 | 2028
Revenue | 1,240 | 1,310 | 1,380 | 1,450
EBITDA at FY2025 | 186 | 186 | 186 | 186
Volume and mix |  | 12 | 25 | 38
Inflation |  | (10) | (21) | (31)
Run costs |  | (3) | (5) | (6)
Transformation levers |  | 32 | 71 | 103
Run-rate EBITDA | 186 | 217 | 256 | 290
EBITDA margin, % | 15.0 | 16.6 | 18.6 | 20.0
Cash turns positive in 2027
In-year savings as phased in the benefit plan, $m
$m, in year | 2026 | 2027 | 2028 | Total
In-year savings | 16 | 51 | 87 | 154
Working capital released | 40 | 62 | 44 | 146
One-off operating cost | (44) | (36) | (18) | (98)
Capital expenditure | (28) | (25) | (14) | (67)
Net cash | (16) | 52 | 99 | 135
Cumulative net cash | (16) | 36 | 135 | 
What the bridge assumes
Volume and mix: revenue grows 5.4% a year to $1,450m on the current portfolio, with no new launches.
Inflation: wages 3.5% and materials 2.5% a year, offset only where index clauses apply.
Run costs: $6m a year for the planning system, the hub's licences and the quality function.
Working capital: $75m from receivables and $71m from inventory, at FY2028 revenue and cost.
Cost to achieve: $165m, $98m of it one-off operating cost and $67m capital; 44% falls in 2026.
Source: Corrin Medical management accounts and transformation plan; FY2025 is eleven months actual and a December forecast. All figures are illustrative, invented for a fictional company.
Four transformation levers +$103m
Volume less inflation and run costs +$1m
$17m
$68m
$21m
$59m
Cost to achieve, $165m in all
Notes: All figures on this page are illustrative: Corrin Medical is a fictional company and every number was invented and computed for this example. Volume alone covers inflation and run costs: $38m against $37m. The levers are the case: $103m of run-rate EBITDA for $165m of cost to achieve, a 20% margin on $1,450m of revenue. Cash turns positive in 2027 because working capital is released early.

## Slide 6: Seven initiatives start by April 2026; the two plant exits run back to back to June 2028
Corrin Medical
Board of Directors | Corrin 2028 operating transformation | 18 December 2025 | Illustrative figures for a fictional company
1
ROADMAP | 2026 TO 2028
Twelve initiatives, January 2026 to December 2028, in order of start
Light petrol: design; petrol: delivery to full run-rate; orange diamonds: milestones; right: deliveries that wait for another initiative or a milestone
2026
2027
2028
Chart: 
| Milestones | P1 Direct-material re-sourcing | C1 Contract-price master, GPO compliance | P3 Indirect spend and freight tender | O2 Spans and layers, commercial and G&A | F3 Lean and OEE in retained plants | C3 Collections and dispute automation | O3 Global quality and regulatory function | P2 BOM value engineering, top 20 SKUs | F1 Salt Lake City exit | O1 Shared-services hub, Brno | C2 Bill-only and consignment digitised | F2 Tuttlingen exit to Brno
Start | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 3 | 6 | 6 | 6 | 9 | 13
Design | 0 | 0 | 4 | 5 | 3 | 4 | 3 | 4 | 4 | 6 | 6 | 6 | 5 | 8
Deliver | 0 | 0 | 14 | 7 | 6 | 5 | 22 | 8 | 9 | 18 | 9 | 18 | 10 | 9
Milestones the board will see reported
M1 January 2026
Programme launch; Transformation Office live
M2 May 2026
Contract-price master live in the US
M3 December 2026
Brno hub opens; validation master plan issued
M4 September 2027
Salt Lake City exit complete
M5 June 2028
Tuttlingen exit complete
M6 December 2028
Full $103m run-rate; programme closes
Source: Corrin Medical management accounts and transformation plan; FY2025 is eleven months actual and a December forecast. All figures are illustrative, invented for a fictional company.
Apr
Jul
Oct
Apr
Jul
Oct
Apr
Jul
Oct
M1
M2
M3
M4
M5
M6
Delivery waits for
O3's validation plan, M3
C1's price master, M3
F1's exit, M4
Notes: All figures on this page are illustrative: Corrin Medical is a fictional company and every number was invented and computed for this example. Dependencies: Salt Lake City line transfers cannot begin until the global quality function has issued the validation master plan at M3; the Brno hub takes over order to cash only on the live price master; Tuttlingen moves after Salt Lake City frees the validation team at M4.

## Slide 7: Five new units and two fewer layers cut G&A from 11.6% to 9.4% of revenue
Corrin Medical
Board of Directors | Corrin 2028 operating transformation | 18 December 2025 | Illustrative figures for a fictional company
1
OPERATING MODEL | 2028
Chief Executive Officer
Transformation Office
Runs the M1 to M6 gates; closes December 2028
Chief Financial Officer
FP&A and treasury
Planning, reporting, capital
New: Global Business Services
Brno: finance and order to cash
Tax and internal control
Group tax, controls, audit liaison
Chief Operating Officer
Five plants
Minneapolis, Juarez, Alajuela, Galway, Brno
New: Supply chain and planning
One plan, inventory, logistics
New: Global procurement
Direct and indirect, from plant buyers
Chief Commercial Officer
Americas
Direct sales, service, distributors
EMEA and Asia-Pacific
Direct sales and 31 distributors
New: Pricing and contracts
Price master, GPO terms, rebates
New: Chief Quality and Regulatory Officer
Moved: Quality system and CAPA
From the COO's plants
Moved: Regulatory affairs
EU MDR and FDA, from R&D
Moved: Post-market surveillance
Complaints, vigilance, from sales
Chief Technology Officer
R&D programmes
Monitoring, infusion, catheters
Moved: Sustaining engineering
From the plants; runs P2
IT and digital
ERP upgrade and planning system
Chief People Officer
HR business partners
Leaders and works councils
Talent and reward
Retention pool for exiting sites
Change and communications
One change network for 2028
Orange outline: new, five in all, counting the quality and regulatory function; petrol outline: moved from another function; grey: unchanged; the Transformation Office closes in December 2028
Three design principles
1
One owner per process end to end: order to cash sits in the Brno hub, not in fourteen countries.
2
Quality and regulatory report to the CEO, independent of the plants they audit.
3
Plants make; procurement, planning and engineering serve all five plants.
Layers, spans and G&A cost
Measure | FY2025 | FY2028
Management layers, CEO to front line | 9 | 7
Average span of control | 4.8 | 7.0
G&A headcount | 1,180 | 990
Back-office locations | 14 | 3
G&A cost ($m) | 143.8 | 136.3
G&A cost, % of revenue | 11.6 | 9.4
Governance to December 2028
Forum | Chair | Meets | Decides
Board | Chair | Quarterly | Passes gates M1 to M6
Transformation committee | CEO | Monthly | Scope, budget and sequence
Transformation Office | Director | Weekly | Plans, risks and benefit tracking
Benefit review | CFO | Monthly | What enters the run-rate
Source: Corrin Medical management accounts and transformation plan; FY2025 is eleven months actual and a December forecast. All figures are illustrative, invented for a fictional company.
Notes: All figures on this page are illustrative: Corrin Medical is a fictional company and every number was invented and computed for this example. New units: Global Business Services in Brno, supply chain and planning, global procurement, pricing and contracts, and the quality and regulatory function reporting to the CEO.

## Slide 8: Mitigation brings all nine risks to ALARP or below; the two worst come from line transfers
Corrin Medical
Board of Directors | Corrin 2028 operating transformation | 18 December 2025 | Illustrative figures for a fictional company
1
RISK | DELIVERY RISKS
Nine risks, before and after mitigation
Likelihood 1 rare to 5 frequent; severity 1 negligible to 5 catastrophic; score is the product
Before mitigation
Likelihood
5
4
R4
R5
R1
3
R3
R6
R8
R7
R2
2
R9
1
1
2
3
4
5
Severity
After mitigation
Likelihood
5
4
3
R4
R8
2
R3
R5
R1
R6
R7
R2
1
R9
1
2
3
4
5
Severity
Acceptable: 5 or less
ALARP: 6 to 12
Unacceptable: 15 or more
R1 and R2 come from moving validated lines. Bridge stock, build-ahead and dual qualification cut their likelihood; severity stays high because a supply gap reaches patients.
Risk register
Mitigation costs $14m in all, inside the $165m; scores before and after mitigation, shaded by zone; owners report monthly
ID | Risk | Owner | Mitigation | Cost, $m | Before | After
R1 | Line re-validation delays the Salt Lake City exit | COO, CQRO | Validation master plan per line; 10 weeks of bridge stock | 2.6 | 16 | 6
R2 | US hospital supply interrupted during line moves | COO | 12-week build-ahead; lines dual-qualified before cut-over | 3.8 | 15 | 8
R3 | GPO renegotiation delays price-master benefits | CCO | Phase by contract renewal date; leakage tracked monthly | 0.4 | 9 | 4
R4 | Order-management upgrade overruns | CFO | Upgrade the current ERP in place; no big-bang replacement | 1.5 | 12 | 6
R5 | Key staff leave the two closing plants early | CPO | $4.2m retention pool; knowledge transfer signed off per line | 4.2 | 12 | 4
R6 | Works-council consultation extends the German exit | CPO | Consultation opens Q1 2027 with 4 months of float | 0.6 | 9 | 6
R7 | EU MDR recertification collides with transfers | CQRO | One regulatory calendar; notified-body slots booked for 2027 | 0.9 | 12 | 6
R8 | Inflation runs above the $31m in the plan | CFO | Index clauses in 70% of supply contracts by 2027 | - | 9 | 6
R9 | Change fatigue lowers sales productivity | CCO | Commercial roles change once, in a single wave | 0.3 | 6 | 2
Risks by zone
Count of risks, and their scores summed
Zone | Before | After
Unacceptable | 2 | 0
ALARP | 7 | 6
Acceptable | 0 | 3
Sum of scores | 100 | 48
What the board will see before a risk lands
Indicators reported monthly by the Transformation Office; a trigger escalates the risk out of cycle
ID | Early-warning indicator | Trigger | Escalates to
R1 | Validation deviations per moved line | More than 2 open per line | Board, next meeting
R2 | US service level, moved product families | Under 95% for 2 weeks | CEO within 48 hours
R3 | Contracts repriced to the renewal plan | Under 80% of plan | CCO and CFO
R4 | Upgrade sprints closed to plan | Under 80% in a quarter | Audit committee
R5 | Regretted leavers at the closing plants | More than 5 in a quarter | CEO and CPO
R6 | Works-council dates met as agreed | Any date 4 weeks late | CEO and CPO
R7 | Notified-body slots confirmed for 2027 | Under 3 confirmed by June | CQRO and CEO
R8 | Supplier price index against the plan | Above plan two quarters | Audit committee
Source: Corrin Medical management accounts and transformation plan; FY2025 is eleven months actual and a December forecast. All figures are illustrative, invented for a fictional company.
Notes: All figures on this page are illustrative: Corrin Medical is a fictional company and every number was invented and computed for this example. Zones follow the ISO 14971 convention the board knows from product risk: acceptable, as low as reasonably practicable, and unacceptable. Owners: COO, CFO, CCO, CPO and the Chief Quality and Regulatory Officer.