## Slide 1: Acres Treated by Method: Statewide; FY2022-FY2026
RSFP.1
Acres treated by method, FY2022 to FY2026
Thousand acres; the total is in the table
Chart: Thousand Acres Treated
| FY2022 | FY2023 | FY2024 | FY2025 | FY2026
Prescribed fire | 9.4 | 12.6 | 16.1 | 19.8 | 23.5
Mechanical thinning | 14.1 | 15.8 | 17.2 | 18 | 18.9
Mastication | 8.2 | 8.9 | 9.6 | 10.1 | 10.4
Hand thinning | 4 | 4.6 | 5.3 | 5.8 | 6.2
Method
◆ Prescribed fire
■ Mechanical thinning
● Mastication
× Hand thinning
Key finding: prescribed fire grew 2.5 times, from 9.4 to 23.5 thousand acres, and passed mechanical thinning in FY2025. It is 40% of FY2026 acres.
Note: Fiscal years run July to June. Hand thinning includes pile burning. An acre treated twice in one year counts twice.
Method | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | Change |  | Rank
All methods | 35.7 | 41.9 | 48.2 | 53.7 | 59.0 | +65% |  | 
Prescribed fire | 9.4 | 12.6 | 16.1 | 19.8 | 23.5 | +150% |  | Rose to 1st
Mechanical thinning | 14.1 | 15.8 | 17.2 | 18.0 | 18.9 | +34% |  | Fell to 2nd
Mastication | 8.2 | 8.9 | 9.6 | 10.1 | 10.4 | +27% |  | Held 3rd
Hand thinning | 4.0 | 4.6 | 5.3 | 5.8 | 6.2 | +55% |  | Held 4th
Illustrative figures. Built in the style of a public US federal presentation; not affiliated with or endorsed by any agency.
Prescribed fire passes mechanical thinning
↑
↓
→
→
Notes: All figures on this page are illustrative: they were invented for a fictional program, the Ridgeline State Forestry Program, and computed and checked in a script. They describe no real agency, county or forest. Acres treated rose 65 percent in five years, from 35.7 to 59.0 thousand; prescribed fire drove most of the growth.

## Slide 2: Hazard and Planned Acres by County; FY2027-FY2029
RSFP.2
Share of county land in wildfire hazard, by hazard class
Percent of county land; counties ranked by the two classes together
Hazard class
Very high
High
Chart: 
| Elk Ridge | Cedar Fork | Granite | Juniper | Hollow Creek | Falcon | Dunmore | Alder | Basin | Ironwood
Very high hazard | 31 | 26 | 22 | 19 | 15 | 12 | 9 | 7 | 4 | 3
High hazard | 27 | 28 | 25 | 24 | 23 | 21 | 19 | 16 | 12 | 9
Homes in the wildland-urban interface (WUI) and acres planned
Thousands, FY2027-FY2029; shares of the ten-county total
County | WUI Homes | Home Share | Planned Acres | Acre Share
Elk Ridge | 18.4 | 12% | 32.0 | 20%
Cedar Fork | 22.1 | 15% | 29.5 | 18%
Granite | 9.8 | 6% | 21.0 | 13%
Juniper | 6.2 | 4% | 16.5 | 10%
Hollow Creek | 14.7 | 10% | 17.5 | 11%
Falcon | 11.3 | 7% | 13.0 | 8%
Dunmore | 25.6 | 17% | 12.5 | 8%
Alder | 8.9 | 6% | 8.0 | 5%
Basin | 30.2 | 20% | 6.0 | 4%
Ironwood | 4.1 | 3% | 4.0 | 2%
All counties | 151.3 | 100% | 160.0 | 100%
Share of WUI homes
Share of planned acres
Chart: 
| Elk Ridge, Cedar Fork | Basin, Dunmore | Other six
Share of WUI homes | 26.8 | 36.9 | 36.4
Share of planned acres | 38.4 | 11.6 | 50
Key finding: Basin and Dunmore hold 37% of the homes in the WUI but receive 12% of planned acres; near homes the plan thins by hand, at 4.8 times the cost per acre of prescribed fire.
Note: Hazard classes are from the program's 2026 fuels model. Bold rows: the two counties with the most WUI homes.
Illustrative figures. Built in the style of a public US federal presentation; not affiliated with or endorsed by any agency.
58%
54%
47%
43%
38%
33%
28%
23%
16%
12%
Both
Notes: All figures on this page are illustrative: they were invented for a fictional program, the Ridgeline State Forestry Program, and computed and checked in a script. They describe no real agency, county or forest. Planned acres follow the hazard rank; the counties with the most homes get few acres because work near homes is done by hand.

## Slide 3: Cost per Acre by Treatment Method: Statewide; FY2026
RSFP.3
Cost per acre treated, by method and by cost component
FY2026 dollars per acre; bar colours as the methods on page 1
Chart: 
| Mechanical thinning | Hand thinning | Mastication | Prescribed fire
Cost per acre | 1610 | 1050 | 700 | 220
Key finding: prescribed fire is 40% of planned acres but 11% of cost; mechanical thinning is 28% of acres and 55% of cost, at 7.3 times the cost per acre, most of it equipment.
Note: Plan cost is planned acres FY2027- FY2029 times FY2026 cost per acre. Bold component: the largest part of the two dearest methods. Hand thinning includes pile burning.
The plan's cost by method, FY2027-FY2029
Thousand acres; dollars per acre; $ million; percent of the plan
Method | Planned Acres | Unit Cost | Plan Cost | Acre Share | Cost Share
Mechanical thinning | 44.0 | 1,610 | 70.8 | 28% | 55%
Hand thinning | 24.0 | 1,050 | 25.2 | 15% | 19%
Mastication | 28.0 | 700 | 19.6 | 18% | 15%
Prescribed fire | 64.0 | 220 | 14.1 | 40% | 11%
All methods | 160.0 | 811 | 129.7 | 100% | 100%
Illustrative figures. Built in the style of a public US federal presentation; not affiliated with or endorsed by any agency.
$610
$820
$180
$95
Labor
$760
$90
$390
$40
Equipment
$150
$60
$70
$25
Materials
$90
$80
$60
$60
Planning
Notes: All figures on this page are illustrative: they were invented for a fictional program, the Ridgeline State Forestry Program, and computed and checked in a script. They describe no real agency, county or forest. The plan's $129.7 million buys 160 thousand acres at an average of $811 an acre.

## Slide 4: Crews and Equipment: Statewide; FY2027-FY2029
RSFP.4
Crews and heavy equipment in service and needed
Count of crews or machines
Resource | In Service FY2026 | Peak Need FY2028 | Gap | Increase
Hand crews (20 people) | 14 | 22 | +8 | +57%
Engine crews | 26 | 30 | +4 | +15%
Qualified burn bosses | 9 | 16 | +7 | +78%
Masticators | 11 | 15 | +4 | +36%
Feller-bunchers | 6 | 9 | +3 | +50%
Skidders | 8 | 11 | +3 | +38%
Crew-days needed and available, by fiscal year
Crew-days; navy is the plan's need, grey what crews can supply
Chart: 
| FY2027 | FY2028 | FY2029
Crew-days needed | 6800 | 8900 | 8300
Crew-days available | 5900 | 7400 | 8500
Lead time to add one unit
Months, longest first
Chart: 
| Qualified burn bosses | Masticators | Feller-bunchers | Skidders | Hand crews (20 people) | Engine crews
Lead time (months) | 18 | 9 | 6 | 5 | 4 | 3
Key finding: capacity is 900 crew-days short in FY2027 and 1,500 at the FY2028 peak. Burn bosses are the tightest constraint: the plan needs 16, up 78% from 9, and each takes 18 months to qualify.
Note: A crew-day is one crew working one day on treatment; engine crews count only days not held for fire response.
Illustrative figures. Built in the style of a public US federal presentation; not affiliated with or endorsed by any agency.
900 short
1,500 short
Notes: All figures on this page are illustrative: they were invented for a fictional program, the Ridgeline State Forestry Program, and computed and checked in a script. They describe no real agency, county or forest. Capacity falls 900 crew-days short in FY2027 and 1,500 in FY2028, and covers the need by FY2029 after hiring.

## Slide 5: Treatment Schedule by Work Stream: FY2027-FY2029
RSFP.5
Work schedule by fiscal quarter, FY2027 to FY2029
July 2026 to June 2029; each bar runs from the first to the last quarter of work
Chart: 
| Permits and environmental review | Crew hiring and burn-boss training | Hand thinning near homes: Dunmore, Basin | Mechanical thinning: Elk Ridge, Cedar Fork | Mastication: Granite, Juniper | Prescribed fire: all high-hazard counties | Other counties: Alder, Falcon, Hollow Creek, Ironwood | Effectiveness monitoring
 | 0 | 1 | 1 | 2 | 3 | 4 | 6 | 8
Scheduled | 3 | 4 | 7 | 9 | 6 | 8 | 6 | 4
Planned acres by year
Thousand acres
Method | FY2027 | FY2028 | FY2029 | Total
Prescribed fire | 16.0 | 22.0 | 26.0 | 64.0
Mechanical thinning | 12.0 | 17.0 | 15.0 | 44.0
Mastication | 8.0 | 11.0 | 9.0 | 28.0
Hand thinning | 6.0 | 9.0 | 9.0 | 24.0
All methods | 42.0 | 59.0 | 59.0 | 160.0
Key finding: mechanical thinning in Elk Ridge and Cedar Fork runs nine of the twelve quarters, Q3 of FY2027 to Q3 of FY2029. FY2027 treats 42.0 thousand acres while permits clear, then 59.0 a year, the FY2026 pace.
Note: Quarter 1 is July to September. Bar colours: the method colours of page 1; grey, preparation and monitoring; navy, the four smaller counties, which use all four methods.
Illustrative figures. Built in the style of a public US federal presentation; not affiliated with or endorsed by any agency.
FY2027
FY2028
FY2029
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Notes: All figures on this page are illustrative: they were invented for a fictional program, the Ridgeline State Forestry Program, and computed and checked in a script. They describe no real agency, county or forest. The schedule front-loads permits and hiring; FY2028 and FY2029 each treat 59 thousand acres.

## Slide 6: Hazard Reduction Expected: Statewide; FY2026-FY2030
RSFP.6
Statewide land in high or very high hazard
Thousand acres; without the plan, fuels keep growing about 1.7% a year
Chart: Thousand Acres
| FY2026 | FY2027 | FY2028 | FY2029 | FY2030
Without the plan | 1240 | 1262 | 1285 | 1306 | 1327
With the plan | 1240 | 1214 | 1168 | 1116 | 1098
Path | FY2026 | FY2027 | FY2028 | FY2029 | FY2030
Without the plan | 1,240 | 1,262 | 1,285 | 1,306 | 1,327
With the plan | 1,240 | 1,214 | 1,168 | 1,116 | 1,098
Acres avoided | 0 | 48 | 117 | 190 | 229
Share of county land in high or very high hazard
Percent of county land; counties in the order of page 2
FY2026
FY2030 with the plan
Chart: 
| Elk Ridge | Cedar Fork | Granite | Juniper | Hollow Creek | Falcon | Dunmore | Alder | Basin | Ironwood
FY2026 | 58 | 54 | 47 | 43 | 38 | 33 | 28 | 23 | 16 | 12
FY2030 with the plan | 37 | 35 | 33 | 30 | 27 | 24 | 20 | 17 | 11 | 9
Key finding: by FY2030 the plan holds high-hazard land to 1,098 thousand acres, 229 thousand (17.3%) below the path without treatment and 11.5% below today. Every county falls, by 3 to 21 points; none stays above 37%.
Illustrative figures. Built in the style of a public US federal presentation; not affiliated with or endorsed by any agency.
229 thousand acres avoided
Notes: All figures on this page are illustrative: they were invented for a fictional program, the Ridgeline State Forestry Program, and computed and checked in a script. They describe no real agency, county or forest. Without treatment, fuel growth adds about 1.7 percent a year to high-hazard land; the plan reverses it.